## Sheet1
Strategy: Subdivision 1 | Time | mth 1 |  |  |  | mth 2 |  |  |  | mth 3 |  |  |  | mth 4 |  |  |  | mth 5 |  |  |  | mth 6 |  |  |  | mth 7 |  |  |  | mth 8 |  |  |  | mth 9 |  |  |  | mth 10 |  |  |  | mth 11 |  |  |  | mth 12
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Available Working Equity | $200k | bar: mth 1 1 to mth 12 4
Prioritise Top 3 | 1-2 weeks | bar: mth 1 1 to mth 1 2
Area Research | 3-4 weeks | bar: mth 1 2 to mth 2 1
Research DA's | 3 weeks | bar: mth 1 4 to mth 2 2
Reverse Feasibility Studies | 3 weeks | bar: mth 1 4 to mth 2 2
Meet Town Planner | 3 weeks | bar: mth 1 4 to mth 2 2
Deal Finding | 3 weeks | bar: mth 1 4 to mth 2 2
Feasibility - Comp Sales | 3 weeks | bar: mth 1 4 to mth 2 2
Meet Target RE Agents | 3 weeks | bar: mth 1 4 to mth 2 2
Feasibility - Costs | 3 weeks | bar: mth 1 4 to mth 2 2
Build A Team | 3 weeks | bar: mth 1 4 to mth 2 2
Research Potential Deals | 7 weeks | bar: mth 1 4 to mth 3 2
Purchase Contract | Variable | bar: mth 2 2 to mth 3 2
Initial Site Survey | 2 weeks | bar: mth 2 2 to mth 2 3
Exchange Contracts | 1 week | bar: mth 2 3
Settlement | 6 weeks | bar: mth 2 3 to mth 3 4
Draft Lots | 3 weeks | bar: mth 2 2 to mth 2 4
Submit DA | 6-9 months | bar: mth 2 4 to mth 8 4
Marketing | Variable | bar: mth 2 4 to mth 8 4
Contractor Quotes | 5 weeks | bar: mth 2 4 to mth 3 4
Public Notification | 3 weeks | bar: mth 8 1 to mth 8 3
Planning Permit | 1 week | bar: mth 8 4
Operational Works | 2 months | bar: mth 8 4 to mth 10 4
Formal Approval Subdivision | 2 weeks | bar: mth 10 3 to mth 10 4
Plan Sealing | 4 weeks | bar: mth 10 3 to mth 11 2
Registering title | 5 weeks | bar: mth 11 2 to mth 12 2
Marketing | Variable | bar: mth 10 4 to mth 12 4
Settlement | bar: mth 12 1 to mth 12 4
Total Money Required |  | mth 1 1: 500; mth 2 1: $50-100k; mth 3 1: $5-10,000; mth 4 1: Holding Costs; mth 5 1: Holding Costs; mth 6 1: Holding Costs; mth 7 1: Holding Costs; mth 8 1: Holding Costs; mth 9 1: $10-50,000; mth 10 1: $5-10,000; mth 11 1: $5-10,000; mth 12 1: $
AWE - End of Month | $ | bar: mth 1 1; mth 2 1; mth 3 1; mth 4 1; mth 7 1; mth 8 1; mth 9 1; mth 10 1; mth 11 1; mth 12 1
Passive Income Created | $ | bar: mth 1 1 to mth 12 4