## Sheet1
Strategy: Subdivision 1 | Time | mth 1 |  |  |  | mth 2 |  |  |  | mth 3 |  |  |  | mth 4 |  |  |  | mth 5 |  |  |  | mth 6 |  |  |  | mth 7 |  |  |  | mth 8 |  |  |  | mth 9 |  |  |  | mth 10 |  |  |  | mth 11 |  |  |  | mth 12
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Available Working Equity | bar: mth 1 1 to mth 12 4
Deal Finding
Area Research
Prioritise Top 3
Research DA's
Meet Town Planner
Feasibility - Costs
Feasibility - Comp. Sales
Reverse Feasibility Studies
Meet Target RE Agents
R/V Potential Deals
Settlement
Purchase Contract
Build A Team
Initial Site Survey
Draft Lots
Public Notification
Submit DA
Contractor Quotes
Pre-approval
Finance - Release Security
Submit DA
Plan Sealing
Registering Title
Marketing
Exchange Contracts
Holding Costs
Total Money Required | $ | bar: mth 1 1; mth 2 1; mth 3 1; mth 4 1; mth 5 1; mth 6 1; mth 7 1; mth 8 1; mth 9 1; mth 10 1; mth 11 1; mth 12 1
AWE - End of Month | $ | bar: mth 1 1; mth 2 1; mth 3 1; mth 4 1; mth 5 1; mth 6 1; mth 7 1; mth 8 1; mth 9 1; mth 10 1; mth 11 1; mth 12 1
Passive Income Created | $ | bar: mth 1 1 to mth 12 4