| ## Multi-Construction Checklist TASK | TIME FRAME | COST |
| --- | --- | --- |
| - Area & Strategy Research | 3mths |  |
| - Speak to local agents about the demand for the end product. |  |  |
| - Meet with your town planner and local council |  |  |
| - Do Feasibility |  |  |
| - Building A Team - Lawyer that specialises in development - Money Lender or Broker - Civil Engineer that will help with design, planning, feasibility and contracting - Town Planner - Architect - Land Surveyor - Hydraulic Engineer - Civil Hydraulic Engineer - Electrical Engineer - Quantity Surveyor (for larger developments) - Landscape Architect - Real Estate Agent / Purchasing Agent - Graphic Artist - Advertising Agency - Surveyor - Body Corp Manager |  |  |
| - Set up Structures |  |  |
| - Deal Finding Stage | 1mth | $1k |
| - Contract on Deal - Negotiating and Acquisition | 2mth | $5k deposit |
| - Due Diligence during contract |  |  |
| - Finance |  |  |
| - Settlement |  | Balance of 20% = $95k, 6% purchase Costs = $30k |
| - DA Prep | 2mth | Design $10k, Townplanner $8k, Civil Plans $5k |
| - DA Lodgement |  | $5k Council Fee |
| - DA Assessment | 3mth | $3k Townplanner & engineer re info request |
| - DA Approval |  |  |
| - Op Works Approval | 2mth | $3k Engineer & $2k Council Fees |
| - Working Drawings | 2mth | Drafty $15k Structural $5k |
| - Building Approval | 1mth | $15k (Certifier, BERS, Plumbing App, Council fees |
| - Build Quotes - Fixed price contract | 3mth |  |
| - Builder Selected & Build Contract Signed |  |  |
| - Finance Application | 2mths | $5k Resi finance, Bank fee |
| - Finance Approval |  |  |
| - Demolition | 1mth | $25k |
| - Construction Phase - Contractors checks - Construction phase - Completion phase | 5mths | $180k total $45k (5% deposit) $90k (10% Base) $45k (15% Frame – Balance paid by bank) |
| - Strata Titling Stage - Survey - Community Management Scheme (CMS) Prep - Plan Sealing - Bank Consent - Titles Dept Lodgement - Titles Registered & Body Corp - First Body Corp Meeting | 2mth | $8k survey $10k Plan sealing, CMS, Titles, Legals $45k Council Contribution (Vic =5% Build) |
| - Off the plan contracts can move to settlement |  |  |
| - Sale - Marketing | 3mth | $6k Staging & Photos $6k Marketing & Adve $6k Off Plan Contracts |
| - Sale - Contracts | 0-3mth | $6k legals |
| - Sale - Settlement |  |  |

Assumptions:

- 1) 3 x Townhouse Development

- 2) Purchase Price - $500k

- 3) Purchase Financing @ 80% LVR hence we contribute 20% - $500k x 20% = $100k Deposit payable by us, Assume $5k on signing contract & balance $95k at Settlement

- 4) Purchase Costs @ 6% = $30k

- 5) Townhouse Construction Costs – 3 townhouses @ $300k each = $900k build cost

- 6) Construction Financing @ 80% Build contract, 20% Our Contribution = $900k x 20% = $180k our contribution. Construction Draw Down Payments – 5% Deposit = $45k, 10% Base = $90k, 15% Frame (but we only need to contribute $45k to bring up to our total $180k).