## Sheet1
Opening Bank Balance |  | $500k |  |  |  | $499k |  |  |  | $484k |  |  |  | $346k |  |  |  | $341k |  |  |  | $338k |  |  |  | $333k |  |  |  | $333k |  |  |  | $318k |  |  |  | $313k |  |  |  | $298k |  |  |  | $293k |  |  |  | $293k |  |  |  | $133k |  |  |  | $88k |  |  |  | $88k |  |  |  | $88k |  |  |  | $80k |  |  |  | $7k |  |  |  | $1k
Strategy: | Time | mth 1 |  |  |  | mth 2 |  |  |  | mth 3 |  |  |  | mth 4 |  |  |  | mth 5 |  |  |  | mth 6 |  |  |  | mth 7 |  |  |  | mth 8 |  |  |  | mth 9 |  |  |  | mth 10 |  |  |  | mth 11 |  |  |  | mth 12 |  |  |  | mth 13 |  |  |  | mth 14 |  |  |  | mth 15 |  |  |  | mth 16 |  |  |  | mth 17 |  |  |  | mth 18 |  |  |  | mth 19 |  |  |  | mth 20 |  |  |  | mth 21 |  |  |  | mth 22 |  |  |  | mth 23 |  |  |  | mth 24
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Available Working Equity | bar: mth 1 1 to mth 24 4
Area & Strategy Research (Done) | 3mth Done
Deal Finding | 1mth | mth 1 1: $1k
Contract on Deal | * | bar: mth 1 4
Site Due Diligence | 2mth | mth 2 1: $5k
Settlement | * | mth 3 4: $125k
DA Prep | 2mth | mth 2 4: $10k; mth 3 4: $13k
DA Lodged | * | mth 4 1: $5k
DA Assessment | 3mth | mth 5 3: $3k
DA Approval | * | bar: mth 6 4
Operational Works Approval | 2mth | mth 6 2: $3k; mth 6 4: $2k
Work Drawings | 2mth | mth 8 4: $15k; mth 9 4: $5k
Building Approval | 1mth | mth 10 2: $15k
Build Quotes | 3mth | bar: mth 9 1 to mth 11 4
Build Contract Signing | * | bar: mth 11 4
Finance application | 2mth | mth 11 4: $5k
Finance approval | * | bar: mth 12 4
Demolition | 1mth | mth 13 4: $25k
Construction | 5mth | mth 13 1: $45k; mth 13 4: $90k; mth 14 3: $45k
Strata titling | 2mth | mth 17 4: $8k; mth 18 1: $10k; mth 18 4: $45k
Sale - Marketing | 3mth | mth 18 1: $6k; mth 18 2: $6k; mth 18 3: $6k
Sale - Contracts | 3mth | bar: mth 17 1 to mth 19 4
Sale - Settlement | * | mth 19 4: $6k
Total Money Required | $499k | mth 1 1: 1k; mth 2 1: 15k; mth 3 1: $138k; mth 4 1: $5k; mth 5 1: 3k; mth 6 1: 5k; mth 7 1: $; mth 8 1: $15k; mth 9 1: $5k; mth 10 1: $15k; mth 11 1: $5k; mth 12 1: $; mth 13 1: $160k; mth 14 1: $45k; mth 15 1: $; mth 16 1: $; mth 17 1: $8k; mth 18 1: $73k; mth 19 1: $6k; mth 20 1: $; mth 21 1: $; mth 22 1: $; mth 23 1: $; mth 24 1: $
AWE - End of Month | $ | mth 1 1: $499k; mth 2 1: 484; mth 3 1: $346k; mth 4 1: $341k; mth 5 1: $338k; mth 6 1: 333; mth 7 1: 333; mth 8 1: $318k; mth 9 1: $313k; mth 10 1: $298k; mth 11 1: $293k; mth 12 1: $293k; mth 13 1: $133k; mth 14 1: $88k; mth 15 1: 88k; mth 16 1: 88k; mth 17 1: $80k; mth 18 1: $7k; mth 19 1: $1k; mth 20 1: $; mth 21 1: $; mth 22 1: $; mth 23 1: $; mth 24 1: $
Passive Income Created | $ | bar: mth 1 1 to mth 24 4