## Sheet1
Assumptions: | Purchase $600k; Borrow 80% @ 3% interest; Cosmetic Reno @ 9%; Sell for $810k
Strategy: Renovation | Time | mth 1 |  |  |  | mth 2 |  |  |  | mth 3 |  |  |  | mth 4 |  |  |  | mth 5 |  |  |  | mth 6 |  |  |  | mth 7 |  |  |  | mth 8 |  |  |  | mth 9 |  |  |  | mth 10 |  |  |  | mth 11 |  |  |  | mth 12
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Available Working Equity | 250000 | mth 1 1: 250000; mth 2 1: 245000; mth 3 1: 245000; mth 4 1: 245000; mth 5 1: 245000; mth 6 1: 185000; mth 7 1: 89600; mth 8 1: 77600; mth 9 1: 83000; mth 10 1: 96000; mth 11 1: 195000; mth 12 1: 444000
Setup Structure |  | mth 1 1: -3000
Loan & Serviceability |  | mth 1 1: -2000
Area & Strategy Research | bar: mth 1 1 to mth 3 4
Deal Finding | bar: mth 3 1 to mth 4 4
Speak to local agents | bar: mth 3 1 to mth 4 4
Confirm End Product/Demand | bar: mth 4 3 to mth 4 4
Feasibility Study | bar: mth 5 1 to mth 5 2
Contract - Deposit paid |  | mth 5 1: -60000
Settlement - Purchase |  | mth 6 1: -96000
Insurance |  | mth 6 2: -2000
A-team - research / engage | bar: mth 3 3 to mth 6 3
Scope of works | bar: mth 5 1 to mth 6 2
Order materials |  | mth 6 1: -5400
Approvals Needed
Renovation work
Demolition / waste / Deposits |  | mth 6 3: -10000
Complete work |  | mth 7 1: -30000; mth 8 1: -8600
Project Management
Staging |  | mth 8 3: -4000
Marketing & Selling |  | mth 9 1: -5000; mth 11 3: -18000; mth 12 1: (Commission)
Contract - (Deposit received) |  | mth 10 2: 81000
Settlement - Sale |  | mth 11 3: 249000
Discharge mortgage |  | mth 11 4: (Pay bank $480k out of sale proceeds)
Managing Agent
Holding Costs |  | mth 6 1: 18000; mth 7 1: 18000; mth 8 1: 18000; mth 9 1: 18000; mth 10 1: 18000; mth 11 1: 18000
Total Money Required | 0 | mth 1 1: -5000; mth 2 1: 0; mth 3 1: 0; mth 4 1: 0; mth 5 1: -60000; mth 6 1: -95400; mth 7 1: -12000; mth 8 1: 5400; mth 9 1: 13000; mth 10 1: 99000; mth 11 1: 249000
AWE - End of Month | 250000 | mth 1 1: 245000; mth 2 1: 245000; mth 3 1: 245000; mth 4 1: 245000; mth 5 1: 185000; mth 6 1: 89600; mth 7 1: 77600; mth 8 1: 83000; mth 9 1: 96000; mth 10 1: 195000; mth 11 1: 444000
Passive Income Created | $ | bar: mth 1 1 to mth 12 4