## Business RE
Motel 10 room - regional - workers, can do tourism
$350k total - $280 builidng $70 business
Strategy: | Time | mth 1 |  |  |  | mth 2 |  |  |  | mth 3 |  |  |  | mth 4 |  |  |  | mth 5 |  |  |  | mth 6 |  |  |  | mth 7 |  |  |  | mth 8 |  |  |  | mth 9 |  |  |  | mth 10 |  |  |  | mth 11 |  |  |  | mth 12
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Available Working Equity | 300000 | mth 1 1: 300000; mth 2 1: 290600; mth 3 1: 287100; mth 4 1: 249600; mth 5 1: 451600; mth 6 1: 122600; mth 7 1: $; mth 8 1: $; mth 9 1: $; mth 10 1: $; mth 11 1: $; mth 12 1: $
Trust structures 1 for building 1 for buisness | 2 weeks | mth 1 1: -6500
Strategist - Broker - let them know - questions - source finance | Continual | mth 2 3: valuation; mth 2 4: -3500; mth 4 2: bank loan; mth 4 4: $210k
DD - Research on Building and Business
business document off agent to accountant for review (current) inc inventory | 3 weeks | mth 1 3: -400
Building documents from the agent (Vendors statement) | 2 weeks | bar: mth 1 1 to mth 1 2
Initial contact and potential soft offer with vendor via agent | 1 week | bar: mth 1 3
Internal lease or contracts to solicitors - verification | 1 week | mth 1 3: -500
Book in Inspections times - Yourself and inspectors | 1 week | mth 1 3: -2000
Negotiations with vendor via agent (post initial inspections) | 5 weeks | mth 2 4: $350k offer accepted
Licence checks and copies of currency (accomodation), (food, grog when applic) | 3 weeks | bar: mth 2 2 to mth 2 4
Clarify Buisness issues with local authorities (Council, police, industry assoc) | 3 weeks | bar: mth 2 2 to mth 2 4
Researching uplifts and clarifying viability, increase income and value | 4 weeks | bar: mth 2 1 to mth 2 4
Capacity - can we reach 90% - How - who to ask - Industry, booking agencies etc | 3 weeks | bar: mth 2 2 to mth 2 4
Contracts to solictors - settlement 60 days (all transfers done by solicitors) | 8 weeks | mth 4 4: -5000
pay deposit | 1 week | mth 3 1: -35000
Insurances in place - building and business | 2 weeks | mth 3 1: -2500
Lease in place between building and business (legal fees to establish) | 3 weeks | mth 4 4: -3000
Workers ?? Arrange to have in place -Interview Manager | 8 weeks | bar: mth 3 1 to mth 4 4
Suppliers accounts in place - Linen, amenities, food, cleaners, power etc | 8 weeks | bar: mth 3 1 to mth 4 4
Check inventory of equipment and supplies | 2 days | bar: mth 4 4
Celebrate - Hand over and settlement (inc stamp duty on building) | 1 week | mth 5 1: -329000
Increase the business - and revalue based on profit
Sell off business and hold property
Hold both
Self manager - and keep both
Total Money Required | $ | mth 1 1: -9400; mth 2 1: -3500; mth 3 1: -37500; mth 4 1: 202000; mth 5 1: -329000; mth 6 1: $; mth 7 1: $; mth 8 1: $; mth 9 1: $; mth 10 1: $; mth 11 1: $; mth 12 1: $
AWE - End of Month | 300000 | mth 1 1: 290600; mth 2 1: 287100; mth 3 1: 249600; mth 4 1: 451600; mth 5 1: 122600; mth 6 1: $; mth 7 1: $; mth 8 1: $; mth 9 1: $; mth 10 1: $; mth 11 1: $; mth 12 1: $
Passive Income Created | $ | bar: mth 1 1 to mth 12 4