## Sheet1
Assumptions: Buy Mullti-tenanted Freehold; 5 Units 1 title, Undermarket Rental Purchase $800K; 70% LVR; 6% Purchase costs; Deposit 10% staggered Strategies applied: Rent to Market; Reno; Strata; Sell 1 and Hold 4
Strategy: Commercial | Time | mth 1 |  |  |  | mth 2 |  |  |  | mth 3 |  |  |  | mth 4 |  |  |  | mth 5 |  |  |  | mth 6 |  |  |  | mth 7 |  |  |  | mth 8 |  |  |  | mth 9 |  |  |  | mth 10 |  |  |  | mth 11 |  |  |  | mth 12
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Available Working Equity |  | mth 1 1: 350000; mth 2 1: 347000; mth 3 1: 296000; mth 4 1: 296000; mth 5 1: 223000; mth 6 1: 4000; mth 7 1: 5000; mth 8 1: 11000; mth 9 1: 267500; mth 10 1: 273100; mth 11 1: 348700; mth 12 1: 354300
Full Strategy Research | 2 weeks | bar: mth 1 1 to mth 1 2
Buyer's Brief set | 1 week | bar: mth 1 2
Holding Cost
Structure Setup | 2 weeks | mth 1 1: 3000
Refine Strategy and Buyer's Brief | bar: mth 1 3
Location Research | 1 -4 weeks | bar: mth 1 4 to mth 2 3
Rental and Sales Comparables | 1 week | bar: mth 2 3
Finance Prep & Feasibility | 1 week | bar: mth 2 3
Proposal/ Offer /Contract |  | mth 2 3: 40000
Offer & Negotiation | 2 weeks | bar: mth 2 3 to mth 2 4
Due Diligence | 2 -6 weeks | mth 2 3: 3000
Valuation | 4-6 weeks | mth 2 3: 3000
Finance Approval | * | bar: mth 4 1
Due Diligence (Agents) | 1-2 weeks | bar: mth 2 3 to mth 2 4
Due Diligence (Property & Lease) | 1-2 weeks | mth 2 3: 5000
Review Feasibility & Final Offer | * | bar: mth 4 1
Deposit Unconditional | * | mth 4 1: 40000
Strata Application | 2 months | mth 4 2: 8000; mth 5 4: 7000
Renovation | 1-2 months | mth 4 2: 25000
Lease - Renegotiation | 2 -4 weeks | mth 5 4: 2000
Marketing (fill vacancy) | 3-6 months | mth 5 1: 4000; mth 6 1: -6000; mth 7 1: -6000; mth 8 1: -6500; mth 9 1: -5600; mth 10 1: -5600; mth 11 1: -5600; mth 12 1: -5600
Settlement Prep | 1 -6 weeks | bar: mth 4 1 to mth 5 2
Settlement | * | mth 5 3: 206000
Marketing (sales) of 1 unit | 1-3 months | mth 6 1: 5000
Sale Settlement |  | mth 8 4: -250000
Refinance at new Value of 4 units | 3 Months | bar: mth 8 1 to mth 10 4
Settlement of Refinance | * | mth 10 4: -70000
Total Money Required | $ | mth 1 1: 3000; mth 2 1: 51000; mth 4 1: 73000; mth 5 1: 219000; mth 6 1: -1000; mth 7 1: -6000; mth 8 1: -256500; mth 9 1: -5600; mth 10 1: -75600; mth 11 1: -5600; mth 12 1: -5600
AWE - End of Month | $ | mth 1 1: 347000; mth 2 1: 296000; mth 3 1: 296000; mth 4 1: 223000; mth 5 1: 4000; mth 6 1: 5000; mth 7 1: 11000; mth 8 1: 267500; mth 9 1: 273100; mth 10 1: 348700; mth 11 1: 354300; mth 12 1: 359900
Passive Income Created | $ | mth 1 1: $; mth 2 1: $; mth 3 1: $; mth 4 1: $; mth 5 1: $; mth 6 1: -6000; mth 7 1: -6000; mth 8 1: -6500; mth 9 1: -5600; mth 10 1: -5600; mth 11 1: -5600; mth 12 1: -5600