Gantt Charts – Worksheet 1 - Demonstration

| Subdivision & Reno Tasks | Time | CP? | Funds $ | Overlap With? |
| --- | --- | --- | --- | --- |
| Deal finding | 1 mth |  |  |  |
| Purchase contract | 1 wk |  | 65,000 |  |
| Due diligence | 1 mth |  | 1,000 |  |
| Purchase Settlement | 1 mth |  | 103,000 |  |
| DA Preparation | 2 mths |  | 18,000 |  |
| DA Lodgement | 1 wk |  |  |  |
| DA Approval | 3 mths |  | 8,000 |  |
| Op Works Approval | 6 wks |  | 5,000 |  |
| Subdivision Quotes | 6 wks |  |  |  |
| Renovation | 6 wks |  | 61,000 |  |
| Subdivision siteworks | 2 mths |  | 39,000 |  |
| Titling | 6 wks |  | 10,000 |  |
| REA Research | 1 mth |  |  |  |
| Comparable Sales | 1 wk |  |  |  |
| Staging/Photos | 2 wks |  | 4,000 |  |
| Appoint REA | 1 wk |  |  |  |
| Sale - Marketing House | 2 mths |  |  |  |
| Sale - Marketing Land | 3 mths |  |  |  |
| Sale - Contract House | 1 wk |  |  |  |
| Sale - Contract Land | 1 wk |  |  |  |
| Sale - Settlement House | 1 mth |  |  |  |
| Sale - Settlement Land | 1mth |  |  |  |

Gantt Charts – Worksheet 2 – Group Activity

Reno and Strata Title 4 Units

Reno & Strata Tasks

Gantt Charts – Project Information – Group Activity

Reno and Strata Title 4 Units

Project Feasibility

| Sale Price $262k/unit | 1,048,000 |
| --- | --- |
| Selling Costs 3% | 32,000 |
| Net Proceeds | 1,016,000 |
| Purchase Price | 739,000 |
| Purchase Costs - 6% | 44,000 |
| Due Diligence | 1,000 |
| Townplanner Council Advice | 1,500 |
| Fire Separation Works | 12,000 |
| Renovation $20k/unit | 80,000 |
| Seal Driveway | 8,000 |
| Building Certifier Fire Sep | 3,000 |
| Surveyor - Plans & Lodge | 10,000 |
| Council Plan Sealing | 2,000 |
| Bank Consent | 500 |
| Bodycorp Docs | 1,500 |
| Surveyor Lodge with Titles | 1,500 |
| Titles Dept | 4,000 |
| Photos for Re-tenanting | 500 |
| Hold Costs for 7mths | 38,000 |
| Total Costs | 946,500 |
| Profit | 69,500 |
| Rental Income | 21,840 |
| Total Profit | 91,340 |

DUE DILIGENCE RESEARCH – Group Activity

Strategy

Vacate units, renovate, re-tenant, strata-title, sell units individually

Past Experience

- Allow 1 month to find Deal

- Allow 1 week to negotiate contract

- Allow 1 month for DD & to get finance approval

- Building & Pest costs $1,000

- Allow 1 month to get quotes & appoint team once unconditional

- Allow 1 month to research & appoint new RE agent to sell the reno'd strata titled units

Broker

- 80% Finance possible

- Allow 1 month Finance Approval

- Allow 1 month to Settlement post finance approval

- At strata titling stage - Bank Consent needs to happen after Plan sealing, will take 2 weeks and cost $500

- 6% Bank Interest

Realestate Agent

- $25k Deposit suggested

- Services are already separate per unit - water and power

- Unit 1 & 3 tenants to vacate Week 1 August (Align settlement with Lease end)

- Unit 2 & 4 tenants to vacate Week 1 October

- To re-sell allow 2 months marketing

- To re-sell make settlement 1 month post titles

Property Manager

- Reno'd units will take 2 weeks to rent

- Reno'd units will achieve a rent of $285/wk after property management costs

- Allow 2 weeks to re-tenant U1&3 after reno & allow $500 for photos

- Allow 2 weeks to re-tenant U2&4 after reno

Townplanner

- During DD Council indicated only strata requirement likely to be to seal the driveway

- Will Take 1 month to get Councils official confirmation on strata requirements

- Townplanner fee $1,500

- Allow 1 week for council to inspect sealed driveway once works are complete, cost is included in Council's plan sealing fee

- Council Plan sealing will take 1 month & Cost $2,000 fee

- No Council Contribution / Headworks fees for strata

Building Certifier

- During DD certifier indicated fire separating walls are block and go to ceiling but not to underside of roof & needs to be remedied

- Will take 2 weeks to provide official advice & cost $3,000

- Need to allow 1 week to do inspection once fire separation works are complete, charge included above

Handyman / Builder

- Fire Separation can be done when Unit 1 & 3 are vacant, will take 2 weeks & cost $12,000

- Allow 1 week between tenants vacate and reno works start

- Budget $20k per unit reno costs & 3 weeks per unit or 6 weeks if doing 2 units together

Concretor - Driveway

- Need Unit 4 to be vacant to do driveway

- 2 weeks to seal driveway & cost $8,000

Surveyor

- Strata Survey & plans can be done after driveway is sealed, allow 1 month & cost $10,000

- Surveyor will lodge docs with Titles Dept once done plan sealing & got bank consent & will cost $1,500

- Title Dept will take 2 weeks and cost $4,000

Body Corporate Manager

- Will prepare the Body Corp Docs, take 1 month, and will do for free if they are appointed Body Corp Manager for first 3 years

- Will arrange Insurance Valuation Report & Sinking Fund Report during Body Corp Docs prep & will cost $1,500

Hold Costs

- Interest @ 80% LVR, 6% interest rate for 7 months, Rates = $3,000, Insurance= $3,000